## Sheet1
Status of IGSTK book Chapters
Kevin Cleary
Last updated 13 July 2006
Note: anyone who authors a chapter should be included on the front page author list
Chapter |  |  |  | status
1 | Introduction | KC | LI | Kevin needs to finish
2 | Getting started | PC | ??? | Kevin check with Patrick - note hello world is also here
3 | Architecture | LI | KG, BB | Kevin Gary to review
4 | Requirements | BB | LI | Kevin to check status with Brian
5 | Software development process | KG | AE | Kevin Gary to finish
6 | State machine | LI | KG | Luis to finish
7 | Events | LI | JJ | Luis to write
8 | Tracker | DG | JZ | James to review, Kevin to send around Word comments from editor
9 | Spatial Object | JJ | ?? | Julien to write, Kevin to send reminder
10 | Spatial Object Representation | JJ | ?? | Julien to write, Kevin to send reminder
11 | View | AE | JJ | Andinet will work some more on this
12 | Logging |  |  | Kevin to ask Hee su if he will write this
13 | ImageIO | AE |  | Andinet will work some more on this
14 | Registration | AE | JZ | James to review
15 | Calibration | JZ | DG | David to review | Kevin to consider sending to Sarah: ask Chris to convert
16 | Hello World | PC |  | seems like a lot for Patrick
17 | Two Views | PC
18 | Four Views | PC
19 | Four Views and Tracking | PC
20 | Four Views and Tracking with CT | PC
21 | Needle Biopsy | PC
22 | Ultrasound Guided RFA | JJ
23 | Deck of Card Robot | PC
Suggested schedule
2006-07-20 | work on your chapters for this meeting
2006-07-27 | chapters due for those who do not have multiple chapters, at least one chapter due for those who have multiple chapters
2006-08-03 | review those chapters
2006-08-10 | all chapters due for those who do have multiple chapters
2006-08-17 | review those chapters
2006-08-24 | final updates to book
2006-08-31 | release of book online, send file to publisher